## Now-Next-Later
Fox021 · template · fox021.com
Product roadmap: now, next, later
One row per item. Fill the fields left to right: the objective, the outcome and the evidence come before the item, so an item without a reason cannot get in.
Evidence is a source you can link, or the word «assumption». An item resting on an assumption goes in as a TEST of that assumption, with a pass line; building waits until the test passes.
Before launch, order by risk: score the risk the item resolves for probability and impact, each 1 to 3. The sheet multiplies them and suggests a horizon: 6 to 9 Now, 3 to 5 Next, 1 to 2 Later. The thresholds are this template's assumption, not a rule; the Horizon column is your decision.
Every item gets one leading metric (a signal you can read within weeks) and one lagging metric (the result itself), and one owner: the person who reports the metric.
The rows marked «example» come from the worked example on the page (a coffee van for film sets). Overwrite them with your own.
Objective (this period, one line) | Outcome for the user | Evidence: a source or «assumption» | Risk it resolves | Probability (1–3) | Impact (1–3) | Risk score (P × I) | Suggested horizon | Item | Type | Pass line (for a test) | Leading metric | Lagging metric | Horizon | Owner | Review date
Example: prove that productions book a coffee van at a day rate | Coordinators ask for a quote | Assumption: no measured demand yet | Nobody books at the day rate | 3 | 3 |  |  | Example: demand test with production coordinators | Test | [the number of quote requests that passes it] | Quote requests per week | Paid bookings per month | Now | The founder
Example: prove that productions book a coffee van at a day rate | The van fills days between productions | Assumption: the check assumes 4 bookings a month | Shoot volume keeps falling, the van may sit idle | 3 | 3 |  |  | Example: booking-volume test | Test | [paid bookings a month that pass it] | Quote requests per week | Paid bookings per month | Now | The founder
Example: prove that productions book a coffee van at a day rate | Unit economics measured on real bookings | Assumption: price, margin and CAC are a category estimate | The numbers are a category estimate | 2 | 3 |  |  | Example: replace the estimated price, margin and CAC with real ones | Test | [the margin per booking that passes it] | Margin per booking | Cost per booked customer | Now | The founder
Example: prove that productions book a coffee van at a day rate | The van can work any shoot site | The county health permit for a mobile food unit | A licence and food safety on each site | 2 | 2 |  |  | Example: licence and food-safety compliance per site | Build |  | Sites cleared before the shoot date | Shoot days worked | Next | The founder

## Timeline
Fox021 · template · fox021.com
Timeline view: the same items by quarter
Use this view when a partner or an investor needs dates, or when one item depends on another. Before launch, keep the Now-Next-Later sheet as the source and copy only the items that need a date here.
Mark the quarters an item runs in with an x. Write the item it depends on, so a failed test shows what it blocks.
Review the timeline at each review date and whenever a Now test finishes: a passed test moves an item, a failed one removes it.
Item | Type (test or build) | Owner | Depends on | Q1 | Q2 | Q3 | Q4 | Status | Next review